## Sheet1
Test Plan
Project Name | Sign Up and Login Testing - Daraz Bangladesh
Prepared By | Md. Tawfiqul Hasan
Date | 2024-09-18
Test Objective | Ensure the Sign-Up and Log-In functionalities operate as expected, providing a secure and user-friendly experience.
In Scope | User registration (Sign Up)
User authentication (Login)
Validation of input fields (email, password)
Forgot password functionality
Social media login integrations
Google account login integrations
Out of Scope | Performance Testing
API Tesing
Multi-factor Authentication(MFA)
Test Deliverables | Test Cases Document
Bug Report
Test Report
Mind Map
Test Matrics
Test Levels | Browser Compatibility Testing
UI Testing
Functionality Testing
Usability Testing
Entry Criteria | Requirements for Sign Up and Login are finalized
Test environment is set up and accessible
Test data (valid/invalid credentials) is ready
Exit Criteria | All critical and high-severity defects are fixed and retested
Test cases for Sign Up and Login executed successfully
Test Environment | Browsers: Chrome, Edge (latest versions)
Operating Systems: Windows 11
Devices: Laptop
Risks and Mitigation | Risk: Requirements may change during testing
Mitigation: Ensure proper communication with the development team and update test cases promptly
Risk: Environment issues may delay testing
Mitigation: Coordinate with the DevOps team for timely setup
Test Schedule | Test Case Design: 18-09-2024 to End Date
Test Environment Setup: 18-09-2024 to End Date
Test Execution: 18-09-2024 to End Date
Bug Reporting and Retesting: 18-09-2024 to End Date
Final Test Report Submission: End Date
Approval
Role | Name | Signature | Date
Test Lead | Tawfiqul Hasan |  | 2024-09-18
Project Manager
QA Engineer